## Roadmap
StudyLog roadmap
Counts come from the Backlog sheet. Edit only the yellow cells (Timeframe, Target).
Milestone | Name | Goal | Timeframe | Target | Items | Done | In progress | Blocked | Open | % done | Status
M0 | Foundations | API, CLI, tests and the first web pages | Done so far
M8 | Design system & redesign | Figma design system and screens, then the web app restyled to match them | Done so far
M9 | Insights | Analytics and Interview ready: APIs and pages | Done so far
M1 | Web: core study loop | A learner can find a path, enroll, study and manage it entirely from the web app | Done so far
M2 | Production launch | CI, deployment and monitoring so the app can run for real users | Next
M3 | Email & accounts | Email provider plus everything that needs email codes | Done so far
M4 | Teams & creators (web) | Web screens for organizations, building your own paths, admin and moderation | Done so far
M5 | Engagement & scale | Reminders, export, pagination and performance as usage grows | Later
M6 | Quality & docs | Stronger tests and documentation | Ongoing
M7 | Mobile app | A mobile app on the same API and schemas | Later
M10 | Platform admin | Superadmin tools to run the platform: users, an overview, organizations and an audit log | Next
M11 | Launch & growth | The first users: official paths to study, outreach, feedback and the numbers that show what works | Next
Total

## Backlog
ID | Title | Description | Area | Milestone | Milestone name | Type | Priority | Size | Status | Depends on | Owner | Target date | Done date | Source | Notes
SL-001 | Monorepo, API and shared packages | Turborepo + Yarn workspaces; NestJS API; schemas, casl, database, logger, nestjs packages | Backend | M0 |  | Feature | P1 | XL | Done |  |  |  | 2026-09-25 | README roadmap
SL-002 | Organizations, accounts and moderation API | Organization management, account settings, path reports and moderation | Backend | M0 |  | Feature | P1 | L | Done |  |  |  | 2026-09-25 | README roadmap
SL-003 | Migration CLI | migration:generate/run/revert/show via nest-commander | Tooling | M0 |  | Feature | P1 | M | Done |  |  |  | 2026-09-25 | README roadmap
SL-004 | Unit tests, 100% coverage and mutation testing | Vitest everywhere, combined coverage report, Stryker | Testing | M0 |  | Chore | P1 | L | Done |  |  |  | 2026-09-26 | README roadmap
SL-005 | Web app with homepage, login and session handling | React + Vite app, API client, session restored from refresh cookie | Frontend | M0 |  | Feature | P1 | M | Done |  |  |  | 2026-09-26 | README roadmap
SL-006 | Signup page | /signup with client-side checks and API errors on fields | Frontend | M0 |  | Feature | P1 | S | Done |  |  |  | 2026-09-28 | README roadmap
SL-007 | Automatic access-token renewal | Retry once after POST /auth/refresh on a 401 with WWW-Authenticate: Bearer | Frontend | M0 |  | Feature | P1 | S | Done |  |  |  | 2026-09-29 | README roadmap
SL-008 | db:seed dummy data | Users, organizations, catalog, enrollments, progress and a month of sessions | Tooling | M0 |  | Feature | P2 | M | Done |  |  |  | 2026-09-29 | README roadmap
SL-009 | Dashboard at /app | Stats, streak, last 30 days, paths with progress, recent sessions | Frontend | M0 |  | Feature | P1 | M | Done |  |  |  | 2026-09-29 | README roadmap
SL-010 | Study sessions page at /app/sessions | History by day; log, edit and delete sessions | Frontend | M0 |  | Feature | P1 | M | Done |  |  |  | 2026-09-29 | README roadmap
SL-011 | Learning path page at /app/paths/:id | Progress at every level, item status, notes and exercises, log time | Frontend | M0 |  | Feature | P1 | M | Done |  |  |  | 2026-10-19 | README roadmap
SL-012 | Catalog page | Browse paths you can see (GET /catalog/paths); filter by source (official, mine, organizations, community) and search | Frontend | M1 |  | Feature | P1 | M | Done |  |  |  | 2026-10-19 | README roadmap
SL-013 | Path preview before enrolling | GET /catalog/paths/:pathId: modules, topics and items of a path, with an Enroll button | Frontend | M1 |  | Feature | P1 | M | Done | SL-012 |  |  | 2026-10-23 | README roadmap
SL-014 | Enroll in a path, optionally choosing parts | POST /me/enrollments with include/exclude rules (e.g. "Arrays, but not Hashing") | Frontend | M1 |  | Feature | P1 | L | Done | SL-013 |  |  | 2026-10-23 | README roadmap
SL-015 | Manage an enrollment | Pause, resume, drop (PATCH status), unenroll, edit rules (PUT .../rules) from the path page | Frontend | M1 |  | Feature | P1 | M | Done | SL-014 |  |  | 2026-10-23 | Proposed
SL-016 | Custom order in a path | Reorder modules, topics and items (PUT .../orders/...), and reset to the admin order | Frontend | M1 |  | Feature | P2 | M | Done |  |  |  | 2026-10-23 | Proposed
SL-017 | Reorder paths on the dashboard | Drag or move paths; PUT /me/enrollments/order | Frontend | M1 |  | Feature | P3 | S | Done |  |  |  | 2026-10-23 | Proposed
SL-018 | Account settings page | Edit name (PATCH /auth/me), change password, delete account | Frontend | M1 |  | Feature | P2 | M | Done |  |  |  | 2026-10-23 | Proposed
SL-019 | Update README intro | Top of README still says apps/web is "empty for now" | Docs | M1 |  | Chore | P3 | XS | Done |  |  |  | 2026-10-23 | Proposed
SL-020 | CI with GitHub Actions | On every push/PR: build, lint, yarn test:cov, migration:generate --check, incremental mutation testing | DevOps | M2 |  | Chore | P1 | M | Done |  |  |  | 2026-10-24 | README roadmap | PRs only: lint, build, unit tests with coverage (posted on the PR) and the Playwright UI tests; turbo and Playwright caching. migration:generate --check and mutation testing moved to SL-080.
SL-021 | Branch protection on master | PRs only, CI must pass, no force pushes (needs GitHub Pro or a public repo) | DevOps | M2 |  | Chore | P2 | XS | Done | SL-020 |  |  | 2026-10-26 | README roadmap | Ruleset (branchruleset.json) active on master, checked through the GitHub API on 2026-10-26: no deletion, no force pushes, PRs only, both CI checks required.
SL-022 | Pre-commit hooks | husky + lint-staged: lint and related tests on committed files | DevOps | M2 |  | Chore | P2 | S | Not started |  |  |  |  | README roadmap
SL-023 | Dockerfile and deployment | Container images, migration:run as a release step | DevOps | M2 |  | Feature | P1 | L | Done |  |  |  | 2026-10-24 | README roadmap | Images built by GitHub Actions to GHCR; deployed on Civo k3s (deploy/civo), live at https://gradiaqo.com. Migrations run in an init container before the API starts.
SL-024 | Check production settings | NODE_ENV=production, COOKIE_SECURE=true, SWAGGER_ENABLED=false, LOG_PRETTY=false, TRUST_PROXY | DevOps | M2 |  | Chore | P1 | S | Done | SL-023 |  |  | 2026-10-24 | README roadmap | deploy/k8s/config.env: production, secure cookies, Swagger off, TRUST_PROXY=2 (Traefik + Caddy). SMTP on port 2525: Civo blocks 25/465/587.
SL-025 | Dependency updates and audit | Dependabot or Renovate; yarn npm audit in CI | DevOps | M2 |  | Chore | P2 | S | Not started | SL-020 |  |  |  | README roadmap
SL-026 | Error tracking | e.g. Sentry for API and web | Operations | M2 |  | Feature | P1 | S | Not started | SL-023 |  |  |  | README roadmap
SL-027 | Graceful shutdown | Close database connections cleanly on deploy | Operations | M2 |  | Chore | P2 | S | Not started |  |  |  |  | README roadmap
SL-028 | Metrics | Request counts, latency, database timing | Operations | M2 |  | Feature | P3 | M | Not started | SL-023 |  |  |  | README roadmap
SL-029 | Rate limits in a shared store | Move counters from memory to e.g. Redis before running more than one API instance | Backend | M2 |  | Chore | P2 | M | Not started |  |  |  |  | README roadmap
SL-030 | Set up an email provider | Resend, SendGrid or Amazon SES; SMTP for development | Backend | M3 |  | Feature | P1 | M | Done |  |  |  | 2026-10-23 | README roadmap
SL-031 | Email verification at signup | OTP/code sent at signup; API + web screen | Backend | M3 |  | Feature | P1 | M | Done | SL-030 |  |  | 2026-10-23 | README roadmap
SL-032 | Password reset | Forgot-password flow; API + web pages | Backend | M3 |  | Feature | P1 | M | Done | SL-030 |  |  | 2026-10-23 | README roadmap
SL-033 | Change your email | Verify the new address before switching | Backend | M3 |  | Feature | P2 | M | Done | SL-030 |  |  | 2026-10-23 | README roadmap
SL-034 | Send invitation emails | Today invited people only see them in GET /me/invitations | Backend | M3 |  | Feature | P2 | S | Done | SL-030 |  |  | 2026-10-23 | README roadmap | Accepting invitations in the web app comes with SL-036
SL-035 | Organizations page | Create, rename and delete organizations; members and roles; leave | Frontend | M4 |  | Feature | P2 | L | Done |  |  |  | 2026-10-23 | Proposed
SL-036 | Invitations in the web app | Owners/admins invite and revoke; users accept or decline (GET /me/invitations) | Frontend | M4 |  | Feature | P2 | M | Done | SL-035 |  |  | 2026-10-23 | Proposed
SL-037 | Build your own learning paths | Create paths, modules, topics and items in your workspace; reorder; private/public | Frontend | M4 |  | Feature | P2 | XL | Done |  |  |  | 2026-10-19 | Proposed
SL-038 | Link global items into your paths | Search GET /catalog/items and link published items into your topics | Frontend | M4 |  | Feature | P3 | M | Done | SL-037 |  |  | 2026-10-19 | Proposed
SL-039 | Report a public path | POST /catalog/paths/:pathId/reports from the catalog | Frontend | M4 |  | Feature | P3 | S | Done | SL-013 |  |  | 2026-10-23 | Proposed
SL-040 | Admin: global catalog editor | Superadmin UI for /admin/catalog: drafts, publish, archive, order | Frontend | M4 |  | Feature | P2 | XL | Done |  |  |  | 2026-10-23 | Proposed
SL-041 | Admin: moderation queue | Review reports (GET /admin/reports): dismiss or hide the path | Frontend | M4 |  | Feature | P3 | M | Done |  |  |  | 2026-10-23 | Proposed
SL-042 | Un-hide a path hidden by mistake | Superadmin clears publicBlockedAt (API) | Backend | M4 |  | Feature | P3 | S | Done |  |  |  | 2026-10-23 | README roadmap
SL-043 | Study reminders / notifications | e.g. "You haven't studied today, keep your streak" | Backend | M5 |  | Feature | P2 | L | Not started | SL-030 |  |  |  | README roadmap
SL-044 | Data export | Users download their progress and study sessions | Backend | M5 |  | Feature | P3 | M | Not started |  |  |  |  | README roadmap
SL-045 | Pagination for paths and enrollments | GET /catalog/paths and GET /me/enrollments return everything today; API + web | Backend | M5 |  | Feature | P2 | M | Not started |  |  |  |  | README roadmap
SL-046 | Batch enrollment progress counting | GET /me/enrollments builds each path tree one by one; batch it | Backend | M5 |  | Chore | P3 | M | Not started |  |  |  |  | README roadmap
SL-047 | Raise mutation scores and set a minimum | Last run: total 71.6%; schemas 10.9%, nestjs 2.8%, database 58.3%. Set thresholds.break | Testing | M6 |  | Chore | P2 | L | Not started |  |  |  |  | README roadmap
SL-048 | Contract snapshot of every schema | Most surviving mutants are in schemas and nestjs | Testing | M6 |  | Chore | P2 | M | Not started |  |  |  |  | README roadmap
SL-049 | Request schemas reject unknown fields | Plus date formats and numeric limits | Testing | M6 |  | Chore | P2 | S | Not started |  |  |  |  | README roadmap
SL-050 | End-to-end tests against a real database | Permissions, visibility, the SQL the unit tests fake | Testing | M6 |  | Chore | P2 | L | Not started |  |  |  |  | README roadmap
SL-051 | Property-based tests | fast-check for enrollment rules and ordering, streaks and dates, slugs | Testing | M6 |  | Chore | P3 | M | Not started |  |  |  |  | README roadmap
SL-052 | Type-check mutants | @stryker-mutator/typescript-checker for more accurate scores | Testing | M6 |  | Chore | P3 | S | Not started |  |  |  |  | README roadmap
SL-053 | Replace starter READMEs | apps/api and apps/cli still have the NestJS starter READMEs | Docs | M6 |  | Chore | P3 | S | Not started |  |  |  |  | README roadmap
SL-054 | Architecture overview | Catalog, enrollments, permissions | Docs | M6 |  | Chore | P3 | M | Not started |  |  |  |  | README roadmap
SL-055 | Mobile app | Choose the stack (e.g. React Native/Expo reusing @studylog/schemas); login, dashboard, log a session, path page | Mobile | M7 |  | Feature | P3 | XL | Not started |  |  |  |  | README roadmap
SL-056 | Design system in Figma | Variables (colors, spacing, radius) with CSS names, text and shadow styles, 21 components and 46 icons in "StudyLog – App Design" | Design | M8 |  | Chore | P1 | L | Done |  |  |  | 2026-10-19 | Figma design
SL-057 | Figma: all web screens | 46 screens: current pages, M1, M3 and M4 screens, loading and error states, dialogs, 390px phone layouts | Design | M8 |  | Chore | P1 | XL | Done | SL-056 |  |  | 2026-10-19 | Figma design
SL-058 | Figma: Analytics and Interview ready | Analytics, Interview ready and the set-a-goal dialog; sidebar gains both links | Design | M8 |  | Chore | P1 | M | Done | SL-056 |  |  | 2026-10-19 | Figma design
SL-059 | Design tokens in code | Replace index.css tokens with the Figma variables (same CSS names), light and dark values, spacing and radius scales | Frontend | M8 |  | Chore | P1 | M | Done | SL-056 |  |  | 2026-10-19 | Figma design
SL-060 | Load Inter and JetBrains Mono | Fonts are not loaded today, so pages use the system font | Frontend | M8 |  | Bug | P1 | XS | Done |  |  |  | 2026-10-19 | Figma design
SL-061 | App shell: sidebar navigation | Dark sidebar: Dashboard, Browse paths, Sessions, Analytics, Interview ready, My paths, Organizations, Admin (superadmins), Settings; account and log out | Frontend | M8 |  | Feature | P1 | M | Done | SL-059 |  |  | 2026-10-19 | Figma design
SL-062 | Phone layout: top bar and menu | 390px: top bar with menu, slide-in navigation, stacked page layouts | Frontend | M8 |  | Feature | P2 | M | Done | SL-061 |  |  | 2026-10-19 | Figma design
SL-063 | Restyle login and signup | Split layout with the dark brand panel | Frontend | M8 |  | Chore | P2 | S | Done | SL-059 |  |  | 2026-10-19 | Figma design
SL-064 | Restyle homepage | Hero with product preview, features, how it works, call to action | Frontend | M8 |  | Chore | P2 | M | Done | SL-059 |  |  | 2026-10-19 | Figma design
SL-065 | Restyle dashboard | Stat tiles, path progress rows, 30-day chart, recent sessions, empty state | Frontend | M8 |  | Chore | P1 | M | Done | SL-061 |  |  | 2026-10-19 | Figma design
SL-066 | Restyle sessions page | Day cards, session rows, log form, inline delete confirmation | Frontend | M8 |  | Chore | P1 | M | Done | SL-061 |  |  | 2026-10-19 | Figma design
SL-067 | Restyle path page | Module cards, topic accordions, item rows with status select, notes and exercises | Frontend | M8 |  | Chore | P1 | M | Done | SL-061 |  |  | 2026-10-19 | Figma design
SL-068 | Loading skeletons and error states | Per the Figma States section | Frontend | M8 |  | Chore | P2 | S | Done | SL-059 |  |  | 2026-10-23 | Figma design | Every page: grey blocks in its shape while loading; errors as the Figma alert with Try again (or Browse paths)
SL-069 | Update UI tests for the redesign | Playwright flows and selectors after the restyle | Testing | M8 |  | Chore | P1 | S | Done | SL-065 |  |  | 2026-10-19 | Figma design
SL-070 | Analytics API | GET /me/analytics?period=&pathId=: time per week and per path, item status, difficulty, study habits, needs-focus topics (no new tables) | Backend | M9 |  | Feature | P1 | L | Done |  |  |  | 2026-10-19 | Figma design
SL-071 | Analytics page | Web page per Figma (Insights · Analytics) | Frontend | M9 |  | Feature | P1 | L | Done | SL-070 |  |  | 2026-10-23 | Figma design
SL-072 | Interview goal | Table and migration (name, date, paths); GET/PUT/DELETE /me/interview-goal | Backend | M9 |  | Feature | P1 | M | Done |  |  |  | 2026-10-19 | Figma design
SL-073 | Readiness API | GET /me/readiness: score (coverage 40, depth 25, revision 15, consistency 20), checks, pace, next steps | Backend | M9 |  | Feature | P1 | L | Done | SL-072 |  |  | 2026-10-19 | Figma design
SL-074 | Interview ready page | Score ring, category checks, next steps, set-a-goal dialog (Figma Insights section) | Frontend | M9 |  | Feature | P1 | L | Done | SL-073 |  |  | 2026-10-23 | Figma design
SL-075 | Tests for insights | Unit tests at 100% coverage; UI tests for Analytics and Interview ready | Testing | M9 |  | Chore | P1 | M | Done | SL-074 |  |  | 2026-10-23 | Figma design | API unit tests done (100%); UI tests come with the pages
SL-076 | Database backups off the server | Nightly pg_dump as a Kubernetes CronJob, uploaded to object storage outside Civo (Cloudflare R2 or Backblaze B2 free tier, or Civo Object Store about $5.43/month); keep 30 days; test a restore | Operations | M2 |  | Feature | P1 | M | Not started | SL-023 |  |  |  | Proposed | The database volume is set to Retain, but that is not a backup. Decide the storage first.
SL-077 | Finish Brevo email authentication | Merge SPF into one record (v=spf1 include:zoho.in include:spf.brevo.com ~all); Authenticate the domain in Brevo; check DKIM and DMARC pass in Gmail ("Show original") | Operations | M2 |  | Chore | P1 | XS | Done |  |  |  | 2026-10-26 | Proposed | Checked in public DNS on 2026-10-26: one SPF record with Zoho and Brevo, DKIM brevo1/brevo2, DMARC and brevo-code all live. Later: DMARC p=none → p=quarantine after a few weeks of clean reports.
SL-078 | Redirect www to gradiaqo.com | www.gradiaqo.com has a CNAME but no certificate or route: add it to the Ingress and certificate, redirecting to the bare domain | DevOps | M2 |  | Bug | P2 | XS | Not started | SL-023 |  |  |  | Proposed
SL-079 | Uptime monitoring | External check on https://gradiaqo.com/health (e.g. UptimeRobot or Better Stack) with email alerts | Operations | M2 |  | Feature | P2 | XS | Not started | SL-023 |  |  |  | Proposed
SL-080 | CI: migration check and mutation testing | The parts of SL-020 not built yet: migration:generate --check (entities and migrations agree) and incremental mutation testing on pull requests | DevOps | M2 |  | Chore | P3 | S | Not started | SL-020 |  |  |  | Proposed
SL-081 | Shorter SMTP timeouts | When the mail server can't be reached, signup waits about 30 s for the connection to time out; set nodemailer connection and greeting timeouts of a few seconds | Backend | M2 |  | Bug | P2 | XS | Not started |  |  |  |  | Proposed | Seen on the first production signup, before SMTP moved to port 2525.
SL-082 | Rebrand the app to Gradiaqo | The web app, page titles, homepage and image names still say StudyLog; emails already say Gradiaqo (BRAND in apps/api/src/mail/templates.ts) | Frontend | M2 |  | Chore | P2 | M | Not started |  |  |  |  | Proposed
SL-083 | CLI: user:promote | yarn cli user:promote <email> (and --demote) to make a superadmin without SQL; documented in deploy/k8s/README.md | Tooling | M10 |  | Feature | P1 | XS | Not started |  |  |  |  | Proposed | The first superadmin was set with a manual UPDATE on 2026-10-24.
SL-084 | Admin users API | GET /admin/users (search by email or name, paginated; verified, role, created, last login if tracked), PATCH platform role, DELETE an account (spam) | Backend | M10 |  | Feature | P1 | M | Not started |  |  |  |  | Proposed
SL-085 | Admin users page | /app/admin/users: search, verified badge, promote or demote superadmin, remove an account with confirmation; sidebar link | Frontend | M10 |  | Feature | P1 | L | Not started | SL-084 |  |  |  | Proposed
SL-086 | Admin platform overview | Sign-ups per day, active learners, verified vs unverified accounts, most-enrolled paths; API and page; becomes the /app/admin landing page (today it redirects to the catalog) | Frontend | M10 |  | Feature | P2 | L | Not started |  |  |  |  | Proposed
SL-087 | Admin organizations oversight | List every organization with its members and paths, for abuse and support requests; API and page | Frontend | M10 |  | Feature | P3 | M | Not started |  |  |  |  | Proposed
SL-088 | Admin audit log | Record who hid, un-hid, published, archived or promoted what and when; a page to browse it | Backend | M10 |  | Feature | P3 | M | Not started |  |  |  |  | Proposed
SL-089 | SEO basics | A title and description per public page (home, login, signup) under the Gradiaqo name; Open Graph and Twitter tags with a 1200×630 share image, so shared links show a card; robots.txt (allow /, disallow /app/) and sitemap.xml served by Caddy; noindex on /app pages; favicon.ico | Frontend | M2 |  | Feature | P2 | M | Not started | SL-082 |  |  |  | Proposed | Today every page is titled "StudyLog", there are no preview tags, and robots.txt and sitemap.xml return the API's 404.
SL-090 | Pre-render the homepage | Render the homepage to static HTML at build time, so search engines and link previews (WhatsApp, LinkedIn, Slack) see its content instead of an empty <div id="root"> | Frontend | M2 |  | Feature | P2 | M | Not started | SL-089 |  |  |  | Proposed
SL-091 | Google Search Console | Verify gradiaqo.com with a DNS TXT record at Hostinger, submit sitemap.xml, check indexing and search queries | Operations | M2 |  | Chore | P2 | XS | Not started | SL-089 |  |  |  | Proposed
SL-092 | Public learning-path pages | Read-only public pages for selected official paths (e.g. DSA, system design) with "Sign up to start": the pages people would find through search. Today the catalog is behind login | Frontend | M5 |  | Feature | P3 | XL | Not started | SL-089 |  |  |  | Proposed | A product decision first: which paths, and how much of each to show logged out.
SL-093 | Dark theme design in Figma | Dark mode for the Figma variables and a pass over the screens (charts, badges, dialogs), so the dark values are designed rather than guessed | Design | M8 |  | Chore | P3 | M | Done | SL-056 |  |  | 2026-10-26 | Proposed | Figma Starter plan allows one mode per collection, so dark is a separate "Color – Dark" collection (same names and CSS names; edit both together), plus Shadow/Dark/* styles and color/bg/scrim. 11 dark screens in Screens – Web › Dark · key screens.
SL-094 | Dark theme in the web app | Follow the system setting by default, with Light / Dark / System in Settings (remembered); set before the first paint so pages don't flash; check every page, chart and dialog in both themes; UI tests for the switch | Frontend | M8 |  | Feature | P2 | M | Done | SL-093 |  |  | 2026-10-26 | Proposed | Settings › Appearance (Light / Dark / System), remembered per browser; src/theme/theme.ts and a pre-paint script in index.html. Dark fixes: accent hover violet/600 (AA), --color-scrim, accent-tint CTA band. Deployed to gradiaqo.com 2026-10-26.
SL-095 | Publish the first official paths | 3–5 interview-prep paths in the admin catalog editor, well ordered with good free resources: DSA (arrays to DP), system design basics, SQL, JavaScript/React or CS fundamentals (OS, DBMS, networks). Quality over quantity | Content | M11 |  | Feature | P1 | L | Not started |  |  |  |  | Proposed | On 2026-10-24 production had 0 learning paths: a new user finds nothing to study. Do this before any outreach.
SL-096 | Feedback link and early-user group | A "Feedback" link in the app (to a form) and a WhatsApp or Telegram group for early users | Frontend | M11 |  | Feature | P1 | XS | Not started |  |  |  |  | Proposed
SL-097 | First 10–30 users, one by one | Personal messages to friends, juniors and ex-colleagues preparing for interviews ("try the DSA path for a week and tell me what's annoying"); watch 3–5 of them sign up and enrol over a call | Marketing | M11 |  | Chore | P1 | M | Not started | SL-095 |  |  |  | Proposed | Before: SL-082 rebrand, SL-089 link previews, SL-077 SPF.
SL-098 | Sign-up source tracking | Keep ?ref= (linkedin, reddit, a college group…) through signup and store it on the account; shown in the admin overview | Backend | M11 |  | Feature | P2 | S | Not started | SL-086 |  |  |  | Proposed
SL-099 | Weekly growth numbers | Every week: sign-ups, activation (verified and enrolled in a path) and week-2 retention (studied again in the second week); fix retention before pushing more traffic | Operations | M11 |  | Chore | P2 | S | Not started | SL-086 |  |  |  | Proposed
SL-100 | Build in public on LinkedIn | A weekly post about building Gradiaqo: features, the stack, the $12/month Civo setup, lessons learned | Marketing | M11 |  | Chore | P2 | S | Not started |  |  |  |  | Proposed | Ongoing.
SL-101 | Posts in developer communities | Useful posts first (e.g. "the DSA order I'd follow for 8 weeks") with the app at the end: r/developersIndia, r/leetcode, college placement-prep WhatsApp/Telegram/Discord groups. Check each community's self-promotion rules | Marketing | M11 |  | Chore | P2 | M | Not started | SL-095 |  |  |  | Proposed
SL-102 | Study groups and coding clubs | Offer clubs and study groups an organization: shared paths and each other's progress. One club admin can bring 30 users | Marketing | M11 |  | Chore | P2 | M | Not started | SL-095 |  |  |  | Proposed
SL-103 | Product Hunt and Peerlist launch | Launch once there are about 50 active users and a few testimonials | Marketing | M11 |  | Chore | P3 | M | Not started | SL-097 |  |  |  | Proposed
SL-104 | Invite a study buddy | Referral: invite a friend to study the same path together; once week-2 retention is good | Frontend | M11 |  | Feature | P3 | M | Not started | SL-099 |  |  |  | Proposed
SL-105 | AI Engineer learning path | An official path for building products on LLMs: how models work, model APIs, prompting, embeddings, RAG, tools and agents (MCP), evals, open models and fine-tuning, production and security, and a capstone. Free resources plus a project in most modules | Content | M11 |  | Feature | P2 | M | In progress | SL-095 |  |  |  | Proposed | content/paths/ai-engineer.yaml: 10 modules, 23 topics, 65 items (15 optional, 12 exercises), about 2–3 months at an hour a day. Passes the importer's parser; all non-YouTube links returned 200 on 2026-10-28, the 5 YouTube links still to check by hand. Next: import on production, check in Admin › Catalog, publish.
SL-106 | System Design learning path | An official path for system design interviews: the 45-minute framework and estimation, networking and APIs, databases (indexes, replication, sharding), caching and CDNs, queues and streams, distributed-systems trade-offs, reliability, 12 classic designs with answer notes, and mock interviews | Content | M11 |  | Feature | P2 | M | In progress | SL-095 |  |  |  | Proposed | content/paths/system-design.yaml: 9 modules, 23 topics, 59 items (9 optional, 16 exercises), about 2 months at an hour a day. Passes the importer's parser; links returned 200 on 2026-10-28 except 3 Cloudflare Learning pages (bot check) and the Instagram sharding post (timed out), still to check by hand. Next: import on production, check in Admin › Catalog, publish.

## How to use
How to use this tracker
Roadmap | Milestones in order. Item counts, % done and status are formulas over the Backlog sheet; fill in only Timeframe and Target (yellow).
Backlog | One row per piece of work. Change Status as you go, and add the Done date when you finish.
Adding an item | Type in the first empty row under the table: it grows automatically. Use the next ID (SL-0xx) and pick a Milestone (M0–M11).
Edit freely | Status, Priority, Size, Owner, Target date, Done date, Notes, Depends on.
Formula column | Milestone name is looked up from the Roadmap sheet; don't type in it.
Status | Not started · In progress · Blocked · Done · Won't do (Won't do is left out of the counts)
Priority | P1 = needed for the current milestone · P2 = should do · P3 = nice to have
Size | XS < half a day · S ≈ 1 day · M ≈ 2–3 days · L ≈ a week · XL = more than a week (rough guesses)
Source | README roadmap = from the Roadmap section of README.md. Proposed = suggested from what the API already supports but the web app doesn't show yet.
Done dates | For M0, taken from the git history.
Figma design | Source "Figma design" = from the design work. Screens: https://www.figma.com/design/OtHkuUtj5AK1MYZYgMEJRH (StudyLog – App Design).

## Lists
Status | Priority | Size | Type | Area
Not started | P1 | XS | Feature | Frontend
In progress | P2 | S | Bug | Backend
Blocked | P3 | M | Chore | Mobile
Done |  | L |  | Design
Won't do |  | XL |  | Testing
DevOps
Operations
Tooling
Docs
Content
Marketing